## S106 Definitions
Northern Arc, Burgess Hill Outline Planning Application S106 Obligations Tracker (Ref DM/23/0747) - Definitions
Term & Meaning (Existing) | Term & Meaning (Proposed) | Page | NOTES
Biodiversity Objective Date means the date 25 years from Commencement of Development. | Biodiversity Objective Date means the date 27 years from Commencement of Development. | 6 | 20 years is the standard timeframe for woodland establishment/maturity, with the full uplift in biodiversity units only realised at that point. So, if the Biodiversity Objective Date (BOD) is March 2046, the planting would need to be completed by March 2026 to align with that maturity period. Given the scale of woodland buffer planting proposed, it is not possible for the full woodland buffer planting to be completed across the Brookleigh site by March 2026. In order to reflect the practicalities of delivering the scale of woodland planting, we request a modest change to the BOD, to allow 27 years between commencement and the BOD. The proposed new date of March 2048 would obviously require the planting to be completed by March 2028, which is realistic. On phased completion of the planting, the woodland buffers will be managed by Homes England or housebuilder partners. Following the transfer of the relevant strategic open spaces to MSDC, the Council will be responsible for the management of the planting to ensure that the full biodiversity gains are realised by the BOD.Would shift Objective Date to 2048 (27 years after commencement in March 2021). See Sch. 7 (Ecology), line 10 LY to review with ecologist
Centre for Outdoor Sport Maintenance Contribution means the financial contribution of nine hundred and fifty thousand and sixteen pounds and nineteen pence (£956,016.19) Index Linked to be applied towards the future maintenance of the Centre for Community Sport and the new facilities to be provided at the triangle | Centre for Outdoor Sport Maintenance Contribution means the financial contribution of nine hundred and fifty thousand and sixteen pounds and nineteen pence (£956,016.19) Index Linked to be applied towards the future maintenance of the Centre for Community Sport and the new facilities to be provided at the triangle and/or towards the delivery of the Sports Facilities.
Planning Application Boundary Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Planning Application Boundary 001 Rev 02 | Planning Application Boundary Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Planning Application Boundary 001 Rev 03 | DoV Dec 22 p.9
Land Use Parameter Plan means the plan appended to the Agreement at Appendix B and with reference: Parameter Plan Land Use 002 Rev 02 | Land Use Parameter Plan means the plan appended to the Agreement at Appendix B and with reference: Parameter Plan Land Use 02 Rev 05 | DoV Dec 22 p.7
Green Infrastructure Parameter Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Green Infrastucture 003 Rev 05 | Green Infrastructure Parameter Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Green Infrastucture 003 Rev 08 | DoV Dec 22 p.7
Access and Movement Parameter Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Access and Movement 004 Rev 04 | Access and Movement Parameter Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Access and Movement 004 Rev 11 | DoV Dec 22 p.7
Density Parameter Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Density 005 Rev 03 | Density Parameter Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Density 005 Rev 04 | DoV Dec 22 p.7
Building Height Parameter Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Building Heights 006 Rev 03 | Building Height Parameter Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Building Heights 006 Rev 06 | DoV Dec 22 p.7
Demolition and Retention Parameter Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Demolition and Retention 007 Rev 02 | Demolition and Retention Parameter Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Demolition and Retention 007 Rev 04 | DoV Dec 22 p.7
Phasing Parameter Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Phasing 008 Rev 02 | Phasing Parameter Plan means the plan appended to this Agreement at Appendix B and with reference: Parameter Plan Phasing 008 Rev 05 | DoV Dec 22 p.7
Mobility Corridor 1 means a pedestrian and cycle route and surrounding areas between A273 Sussex Way at the junction with Marchants Way and Wolstonbury Way, as well as pedestrian and cycle improvements on routes from Freeks Lane to Farm to Wivelsfield station and to Burgess Hill station. | Mobility Corridor 1 means a pedestrian and cycle route and surrounding areas between A273 Sussex Way at the junction with Marchants Way and Wolstonbury Way, as well as pedestrian and cycle improvements on routes from Freeks Lane to Farm to Wivelsfield station and to Burgess Hill station. | DoV Dec 22 p.7 | Refer to updated plan prepared by AECOM 60610807-ACM-00-XX-SK-CE-0006 Mobility Corridors Phasing Complementing Proposed s106 Deed of Variation 3
Mobility Corridor 2 means a pedestrian and cycle route between Gatehouse Lane from A273 Jane Murray Way and Wolstonbury Way, as well as pedestrian and cycle improvements linking Mobility Corridor 1 at the junction between London Road and Maple Drive. | Mobility Corridor 2 means a pedestrian and cycle route between Gatehouse Lane from A273 Jane Murray Way and Wolstonbury Way, as well as pedestrian and cycle improvements linking Mobility Corridor 1 at the junction between London Road and Maple Drive to Wivelsfield Station. | 19 | Refer to updated plan prepared by AECOM 60610807-ACM-00-XX-SK-CE-0006 Mobility Corridors Phasing Complementing Proposed s106 Deed of Variation 3
OS1.14a - new definition | OS1.14a means the land identified on the Open Space Transfer Plan comprising not less than 0.1 hectares of semi-natural green space | DoV Dec 22 p.9
OS1.14b - new definition | OS1.14b means the land identified on the Open Space Transfer Plan comprising not less than 0.04 hectares of semi-natural green space
Planning Permission means the planning permission granted by the District Council pursuant to the Application substantially in the draft form annexed at Appendix A. | Planning Permission means the planning permission granted by the District Council pursuant to the Application substantially in the draft form annexed at Appendix A and/or the Section 73 Planning Permission (as appropriate). | DoV Dec 22 p.10
Community Building 1 means (a) a stand-alone multi-use flexible community building of not less than 500 sqm (GEA); and (b) associated car parking and outdoor amenity space, to be provided within Sub-Phase P1.4 as shown on the Land Use Parameter Plan and in accordance with the Community Building 1 Specification | Community Building 1 means (a) a stand-alone multi-use flexible community building of not less than 500 sqm (GEA); and (b) associated car parking and outdoor amenity space, to be provided within Sub-Phase P1.4 as shown on the Land Use Parameter Plan and in accordance with the Community Building 1 Specification
Community Building 2 means: a) A stand-alone multi-use flexible community building of not less than 1,0 900 sqm (GEA); and b) Associated car parking and outdoor amenity space. | Community Building 2 means: a) A stand-alone multi-use flexible community building of not less than 900 sqm (GEA); and b) Associated car parking and outdoor amenity space.
Community Engagement Worker Funding - new definition | Community Enagement Worker funding refers to funding being widened to allow any money not spent on the community engagement worker to be spent on wider community engagement activities.
Green circle maintenance contribution - new definition | Green circle maintenance contribution relates to the maintenance contribution to be paid to WSCC for all of the Green Circle as PROW (bridleway)

## Sch1 Phasing
Northern Arc, Burgess Hill Outline Planning Application S106 Obligations Tracker (Ref DM/23/0747) - Schedule 1, Phasing
Obligation Topic | Obligation wording | Proposed Obligation wording | Schedule | Reference (Paragraph No.) | Page | Notes
Phasing | The Owner shall submit to the District Council for approval in writing the Specification for the Green Superhighway Eastern Link and Bridge prior to the commencement of Sub-Phase OS1.2S | The Owner shall submit to the District Council for approval in writing the Specification for the Green Superhighway Eastern Link and Bridge prior to the commencement of Sub-Phase 1.2 (Eastern Primary School) | Schedule 1 | 1.3 | DoV Jan 21 p.14 | Specification linked to delivery of Primary School (by Homes Englands), rather than open space in Phase 1C.

## Sch2 Open Space
Northern Arc, Burgess Hill Outline Planning Application S106 Obligations Tracker (Ref DM/23/0747) - Schedule 2, Open Space
Obligation Topic | Obligation wording | Proposed Obligation wording | Schedule | Reference (Paragraph No.) | Page | Notes
Open Space | Green Circle Maintenance Contribution | *To be discussed with MSDC and WSCC (Countryside team) in relation to areas that fall inside and outside the designated OS.* |  |  |  | Maintenance contribution for WSCC for all of the Green Circle as PROW (in addition to Open Space contribution to MSDC)

## Sch2 Open Space triggers
Northern Arc, Burgess Hill Outline Planning Application S106 Obligations Tracker (Ref DM/23/0747) - Schedule 2, Open Space Triggers
Open Space | Approval of Specification Trigger | Transfer to MSDC Trigger (Existing) | Transfer to MSDC Trigger (Proposed) | S106 Reference | Notes
Western Parkland | Sub-Phase WP | Occupation of 90% of the Dwellings within Sub-Phase P1.4 | Prior to occupation of 25% of dwellings within Sub-Phase 2.1 and Sub-Phase 2.3 combined. | DoV Jan 2021 (P.17) | New trigger linked to Sub-Phase 2A (assumed that 2A developer will deliver Western Park). New trigger would be circa December 2031. Amended to 65%.
OS1.10 | Sub-Phase OS1.10 | Occupation of 90% of the Dwellings within Sub-Phase P1.4 | Prior to occupation of 65% of dwellings within Sub-Phase 2.1 and Sub-Phase 2.3 combined, the Green Circle within Open Space Area OS.1.10 is constructed. Prior to occupation of 90% of dwellings within Sub-Phase 4.1 OS1.10 is transferred to the MSDC. | DoV Jan 2021 (P.17)
OS1.14a | Sub-Phase OS1.14 | Occupation of 90% of the Dwellings within Sub-Phase P1.9 | Occupation of 90% of the Dwellings within Sub-Phase P1.9. | DoV Jan 2021 (P.18) | This was originally one obligation (OS1.14) and its been split out, but the triggers remain the same.
OS.1.14b |  | Occupation of 90% of the Dwellings within Sub-Phase P1.10 | Occupation of 90% of the Dwellings within Sub-Phase P1.10.

## Sch4 Sport Leisure Community
Northern Arc, Burgess Hill Outline Planning Application S106 Obligations Tracker (Ref DM/23/0747) - Schedule 4, Sports Leisure Community
Obligation Topic | Obligation wording | Proposed Obligation wording | Schedule | Reference (Paragraph No.) | Reference for previous DoV amendments | Notes
Community Buildings | Prior to the Occupation of 201 Dwellings to Transfer Community Building 2 to the District Council or its nominee and not to Occupy 201 Dwellings unless and until Community Building 2 has been Transferred to the District Council. | Prior to the Occupation of 90% of the dwellings in sub phases P1.7 and P1.8, P1.5, P1.6 and P1.3 combined and prior to any occupations of other residential parcels to the east of Cuckfield Road to Transfer Community Building 2 to the District Council or its nominee and not to Occupy more than 90% Dwellings in sub phases P1.3,P1.5, P1.6, P1.7 and P1.8 combined and prior to any occupations of other residential parcels to the east of Cuckfield Road unless and until Community Building 2 has been Transferred to the District Council. | Schedule 4 Part 2 | 2.19 | DoV Jan 21 p.25 | By our calculation, this trigger would now equate to 450 homes being occupied east of Isaacs Lane by 100% of Phase 1B and 75% of Phase 1C.
Community Buildings | Not to Occupy more than 201 dwellings or 50% dwellings in sub phases P1.7 and P1.8 combined, unless and until a Certificate of Practical Completion has been issued in respect of Community Building 2 | Not to Occupy more than 90% of the dwellings in sub phases P1.7 and P1.8, P1.5, P1.6 and P1.3 combined, unless and until a Certificate of Practical Completion has been issued in respect of Community Building 2 | Schedule 4 Part 2 | 2.16 | DoV Jan 21 p.24 | By our calculation, this trigger would now equate to 450 homes being occupied east of Isaacs Lane by 100% of Phase 1B and 75% of Phase 1C.
Community Buildings | To provide Community Building 2 in accordance with the Community Building 2 Specification and to secure a Certificate of Practical Completion and make available Community Building 2 for public use prior to Occupation of 201 of the Dwellings or 50% of the dwellings in sub phases P1.7 and P1.8 combined | To provide Community Building 2 in accordance with the Community Building 2 Specification and to secure a Certificate of Practical Completion and make available Community Building 2 for public use prior to Occupation 90% of the dwellings in sub phases P1.7 and P1.8, P1.5, P1.6 and P1.3 combined. | Schedule 4 Part 2 | 2.15 | DoV Jan 21 p.24 | By our calculation, this trigger would now equate to 450 homes being occupied east of Isaacs Lane by 100% of Phase 1B and 75% of Phase 1C.
Community Buildings | To provide Community Building 1 in accordance with the Community Building 1 Specification and to secure a Certificate of Practical Completion and make available Community Building 1 for public use prior to Occupation of 884 of the Dwellings | To provide Community Building 1 in accordance with the Community Building 1 Specification and to secure a Certificate of Practical Completion and make available Community Building 1 for public use prior to Occupation of 75% dwellings in Sub-Phase P1.4 and P1.9 combined. | Schedule 4 Part 2 | 2.13 | DoV Jan 21 p.23
Community Buildings | Not to Occupy 884 of the Dwellings unless and until a Certificate of Practical Completion has been issued in respect of Community Building 1 | Not to Occupy more than 75% of Dwellings within Sub-Phase P1.4 and P1.9 combined unless and until a Certificate of Practical Completion has been issued in respect of Community Building 1 | Schedule 4 Part 2 | 2.14 | DoV Jan 21 p.23
Community Buildings | Prior to the Occupation of 1004 Dwellings to Transfer Community Building 1 to the District Council or its nominee and not to Occupy 1004 Dwellings unless and until Community Building 1 has been Transferred to the District Council. | Prior to the Occupation of 75% of Dwellings within Sub-Phase P1.4 and P1.9 combined, 25% of dwellings wtihin sub-phase 2.1 and 2.3 and prior to any occupations of other residential parcels to the west of Cuckfield Road to Transfer Community Building 1 to the District Council or its nominee and not to Occupy more than 75% of Dwellings within Sub-Phase P1.4 and P1.9 combined. 25% of dwellings within sub-phase 2.1 and 2.3 and prior to any occupation of other residential parcels to the west of Cuckfield Road unless and until Community Building 1 has been Transferred to the District Council. | Schedule 4 Part 2 | 2.18 | DoV Jan 21 p.24
Sport & Leisure | Following completion of the Inspection and Certification Procedure set out in Schedule 3 above: (a) to Transfer the CfOS Phase 1 Land to the District Council or its nominee on or before 31 March 2023; and (b) to Transfer the CfOS Phase 2 Land to the District Council or its nominee on or before 31 March 2024. | Following completion of the Inspection and Certification Procedure set out in Schedule 3 above: (a) to Transfer the CfOS Phase 1 Land to the District Council or its nominee on or before 31 March 2023; and (b) to Transfer the CfOS Phase 2 Land to the District Council or its nominee on or before 1st September 2027. | Schedule 4 Part 1 | 1.6 | DoV Dec 22 p.18
Community Buildings | Not to Commence Sub-Phase P1.7 or Sub-Phase P1.8 unless and until the Community Building 2 Specification has been approved in writing by the District Council | Not to occupy Sub-Phase P1.7 or Sub-Phase P1.8 unless and until the Community Building 2 Specification has been approved in writing by the District Council and prior to commencement of the Community Centre development. | Schedule 4 Part 2 | 2.11 | DoV Jan 21 p.23

## Sch 5 Community Engagement
Northern Arc, Burgess Hill Outline Planning Application S106 Obligations Tracker (Ref DM/23/0747) - Schedule 5, Community Engagement
Obligation Topic | Obligation wording | Proposed Obligation wording | Schedule | Reference (Paragraph No.) | Page | Notes
Community Engagement Worker Funding | N/A - New Obligation. | Funding to be widened to allow any money not spent on the community engagement worker to be spent on community engagement activities.

## Sch6 Local Centres Employment
Northern Arc, Burgess Hill Outline Planning Application S106 Obligations Tracker (Ref DM/23/0747) - Schedule 6, Local Centres Employment
Obligation Topic | Obligation wording | Proposed Obligation wording | Schedule | Reference (Paragraph No.) | Page | Notes
Employment Land | To submit for the written approval of the District Council the Employment Land Scheme prior to Occupation of more than 99 Dwellings. | To submit for the written approval of the District Council the Employment Land Scheme prior to Occupation of more than 200 Dwellings. | Schedule 6 Part 5 | 5.1 | 62
Employment Land | Not to Occupy more than 99 Dwellings until the Employment Land Scheme has been approved by the District Council | Not to Occupy more than 200 Dwellings until the Employment Land Scheme has been approved by the District Council | Schedule 6 Part 5 | 5.2 | 62

## Sch8 Affordable Housing
Northern Arc, Burgess Hill Outline Planning Application S106 Obligations Tracker (Ref DM/23/0747) - Schedule 8, Affordable Housing
Obligation Topic | Obligation wording | Proposed Obligation wording | Schedule | Reference (Paragraph No.) | Page | Notes
Affordable Housing | To provide the Affordable Extra Care Housing within Phase 1 and not to Commence Phase 2 unless and until: (a) the Affordable Extra Care Facility has been constructed and made ready for use (and all the Affordable Extra Care Units within it have been made ready for residential occupation) in accordance with the Planning Permission and relevant Approved Affordable Housing Scheme; and (b) all of the Affordable Housing Land upon which the Affordable Extra Care Facility is to be provided and the Affordable Extra Care Units has been Transferred to the Registered Provider. | To provide the Affordable Extra Care Housing within Phase 1 and not to occupy Phase 2 unless and until: (a) the Affordable Extra Care Facility has been constructed and made ready for use (and all the Affordable Extra Care Units within it have been made ready for residential occupation) in accordance with the Planning Permission and relevant Approved Affordable Housing Scheme; and (b) all of the Affordable Housing Land upon which the Affordable Extra Care Facility is to be provided and the Affordable Extra Care Units has been Transferred to the Registered Provider. | Schedule 8 Part 2 | 2.2 | 65

## Sch9 G&T
Northern Arc, Burgess Hill Outline Planning Application S106 Obligations Tracker (Ref DM/23/0747) - Schedule 9 Gypsy and Traveller
Obligation Topic | Obligation wording | Proposed Obligation wording | Schedule | Reference (Paragraph No.) | Page | Notes
Gypsy Traveller | To submit for the written approval of the District Council the Gypsy and Traveller Phase 1 Site Specification prior to Occupation of any Dwelling; | To submit for the written approval of the District Council the Gypsy and Traveller Phase 1 Site Specification prior to Occupation of 250 dwellings. | Schedule 9 | 1.1 | 70
Gypsy Traveller | Not to Occupy any Dwelling until the Gypsy and Traveller Phase 1 Site Specification has been approved by the District Council | Not to Occupy the 300th dwelling until the Gypsy and Traveller Phase 1 Site Specification has been approved by the District Council. | Schedule 9 | 1.2 | 70

## Sch12 Off-site Highways
Northern Arc, Burgess Hill Outline Planning Application S106 Obligations Tracker (Ref DM/23/0747) - Schedule 12 Part 8, Off-site Highways
Works | Development Threshold and Conditions | Proposed Development Threshold and Conditions | Reference | Schedule | Page | Notes
Mobility Corridor 1 | Prior to commencement of development on Plots 1.1, 1.2, 1.5, 1.6, 1. 7 or 1.8, details of Mobility Corridor 1 shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plots 1. 1, 1. 2, 1. 5, 1. 6, 1. 7 or 1. 8 unless and until details of Mobility Corridor 1 have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of any land use on Plots 1.1, 1.2, 1.5, 1.6, 1.7 or 1. 8, Mobility Corridor 1 shall be constructed. Not to occupy any land use on Plots 1.1, 1.2, 1.5, 1.6, 1. 7 or 1.8 unless and until Mobility Corridor 1 has been constructed. | Prior to occupation of 175 dwellings in P1.5, P1.6, P1.7 & P1.8 and prior to occupation of P1.1 and P1.2 details of Mobility Corridor 1 shall be submitted for approval to the local planning authority. Development shall be carried out in accordance with the approved details. Prior to occupation of 300 dwellings in P1.5, P1.6, P1.7 & P1.8 and prior to occupation of P1.1 and P1.2, Mobility Corridor 1 shall be constructed. Not to occupy more than 300 dwellings in P1.5, P1.6, P1.7 & P1.8 and prior to occupation of P1.1 and P1.2 unless and until Mobility Corridor 1 has been constructed. | OPA Drawing: 60578790_MC_001 | Schedule 12, Part 8 | DoV Dec 22 p.22 & 23
Leylands Road/Leylands Park Improvement Scheme | Prior to occupation of any dwelling on Plots 1.5, 1.6, 1.7 or 1.8, the Leylands Road/Leylands Park improvements shall be implemented. Not to occupy any dwellings on Plots P1.5, 1.6, 1.7 or 1.8 unless and until the Leylands Road/Leylands Park improvements have been implemented. | Prior to occupation of the 200th dwelling on Plots 1.5, 1.6, the Leylands Road/Leylands Park improvements shall be implemented. Not to occupy the 200th dwelling on Plots P1.5, 1.6, unless and until the Leylands Road/Leylands Park improvements have been implemented. | Drawing from Transport Assessment Addendum: 60578790-ACM-XX-XX-DR-CE-000145 | Schedule 12, Part 8 | 97
Leylands Park Parking Management Scheme | Prior to occupation of any dwelling on Plots 1.5, 1.6, 1.7 or 1.8, the Leylands Park Parking Management Scheme shall be implemented. Not to occupy any dwellings on Plots 1.5, 1.6, 1.7 or 1.8 unless and until the Leylands Park Parking Management Scheme have been implemented. | Prior to occupation of the 50th dwelling on Plots 1.7 or 1.8, the Leylands Park Parking Management Scheme shall be implemented. Not to occupy the 50th dwelling on Plots 1.7 or 1.8, unless and until the Leylands Park Parking Management Scheme have been implemented. | Drawing from Transport Assessement Addendum: 60578790_DP_LPPC | Schedule 12, Part 8 | 98
Fairbridge Way Pedestrian Cycle Access | Prior to commencement of development on Plots 1.7 and 1.8, details of the Fairdbridge Way Pedestrian Cycle Access shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plots 1. 7 or 1. 8 unless and until details of the Fairbridge Way Pedestrian Cycle Access have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of any development on Plots 1. 7 or 1. 8, the Fairbridge Way Pedestrian Cycle Access shall be constructed. Not to occupy any development on Plots 1. 7 or 1. 8 unless and until the Fairbridge Way Pedestrian Cycle Access has been constructed. | Prior to commencement of above ground works of buildings on Plots 1.7 and 1.8, details of the Fairbridge Way Pedestrian Cycle Access shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence above ground works of buildings on Plots 1. 7 or 1. 8 unless and until details of the Fairbridge Way Pedestrian Cycle Access have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to occupation of the 10th dwelling on Plots 1. 7 or 1. 8 the Fairbridge Way Pedestrian Cycle Access shall be constructed. Not to occupy the 10th dwelling on Plots 1. 7 or 1. 8, unless and until the Fairbridge Way Pedestrian Cycle Access has been constructed. | Drawing from OPA: 60578790-ACM-XX-XX-DR-CE-000121 | Schedule 12, Part 8 | DoV Dec 22 p.21 & 22
A2300 Traffic Calming | Prior to commencement of development on Plot 1.4 details of a scheme to implement a toucan crossing on the western arm of the A2300/Northern Arc Avenue roundabout and associated works shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plot 1.4 unless and until details of the scheme to implement a toucan crossing on the western arm of the A2300/Northern Arc avenue roundabout and associated works have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of any development on Plot 1.4, the A2300 Traffic Calming shall be constructed. Not to occupy any development on Plot 1.4 unless and until the A2300 Traffic Calming has been constructed. | Prior to commencement of development on Plot 1.4 details of a scheme to implement a toucan crossing on the eastern arm of the A2300/Northern Arc Avenue roundabout and associated works shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plot 1.4 unless and until details of the scheme to implement a toucan crossing on the eastern arm of the A2300/Northern Arc avenue roundabout and associated works have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of any development on Plot 1.4, the A2300 Traffic Calming shall be constructed. Not to occupy any development on Plot 1.4 unless and until the A2300 Traffic Calming has been constructed. | Drawing from OPA: 60578790-ACM-XX-XX-DR-CE-000103 | Schedule 12, Part 8 | 98
Gatehouse Lane Pedestrian Cycle Access | Prior to commencement of development on Plot 1.4 details of the Gatehouse Lane Pedestrian Cycle Access shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plot 1.4 unless and until details of the Gatehouse Lane Pedestrian Cycle Access have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of any dwellings on Plot 1.4 the Gatehouse Lane Pedestrian Cycle Access shall be constructed. Not to occupy any dwellings on Plot 1.4 until the Gatehouse Lane Pedestrian Cycle Access has been constructed. | Prior to commencement of development on Plot 1.4 details of the Gatehouse Lane Pedestrian Cycle Access shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plot 1.4 unless and until details of the Gatehouse Lane Pedestrian Cycle Access have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of the 50th dwelling on Plot 1.4, the Gatehouse Lane Pedestrian Cycle Access shall be constructed. Not to occupy the 50th dwelling on Plot 1.4, until the Gatehouse Lane Pedestrian Cycle Access has been constructed. | 60578790-ACM-XX-XX-DR-CE-000139 | Schedule 12, Part 8 | 100
Mobility Corridor 2 | Prior to commencement development on Plots 1.4, 1.9, 1.10 or 1.11, details of Mobility Corridor 2 shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plots 1.4, 1.9, 1.10 or 1.11 unless and until details of Mobility Corridor 2 have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of any land use on Plots 1.4, 1.9, 1.10 or 1.11, Mobility Corridor 2 shall be constructed. Not to occupy land use on Plots 1.4, 1.9, 1.10 or 1.11 unless and until Mobility Corridor 2 has been constructed. | Prior to first occupation of dwellings on Plots 1.4 and 1.9 details of Mobility Corridor 2 shall be submitted for approval to the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of 150 dwellings on Plots 1.4 and 1.9 Mobility Corridor 2 shall be constructed. | OPA Drawing: 60578790_MC_002 | Schedule 12, Part 8 | 101
Mobility Corridor 3 | Prior to commencement development on Plots 1.4, 1.9, 1.10 or 1.11, details of Mobility Corridor 3 shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plots 1.4, 1.9, 1.10 or 1.11 unless and until details of Mobility Corridor 3 have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of any land use on Plots 1.4, 1.9, 1.10 or 1.11, Mobility Corridor 3 shall be constructed. Not to occupy land use on Plots 1.4, 1.9, 1.10 or 1.11 unless and until Mobility Corridor 3 has been constructed. | Prior to occupation of 250 dwellings site wide, details of Mobility Corridor 3 shall be submitted for approval to the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of 450 dwellings site-wide, Mobility Corridor 3 shall be constructed. |  | Schedule 12, Part 8 | 101
Mobility Corridor 4 | Prior to commencement development on Plots 1.4, 1.9, 1.10 or 1.11, details of Mobility Corridor 4 shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plots 1.4, 1.9, 1.10 or 1.11 unless and until details of Mobility Corridor 4 have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of any land use on Plots 1.4, 1.9, 1.10 or 1.11, Mobility Corridor 4 shall be constructed. Not to occupy land use on Plots 1.4, 1.9, 1.10 or 1.11 unless and until Mobility Corridor 4 has been constructed. | Prior to occupation of 350 dwellings site wide, details of Mobility Corridor 4 shall be submitted to for approval to the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of 550 dwellings site-wide, Mobility Corridor 4 shall be constructed. | OPA Drawing: 60578790_MC_003 | Schedule 12, Part 8 | 101
Jane Murray Way Footway Improvements | Prior to commencement of development on Plots 1.4, 1.9, 1.10 or 1.11, details of the Jane Murray Footway Improvements shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plots 1.4, 1.9, 1.10 or 1.11 unless and until details of the Jane Murray Footway Improvements have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of any land use on Plots 1.4, 1.9, 1.10 or 1.11, the Jane Murray Footway Improvements shall be constructed. Not to occupy land use on Plots 1.4, 1.9, 1.10 or 1.11 unless and until the Jane Murray Footway Improvements has been constructed. | Prior to commencement development on Plots 1.4 and 1.9, details of Jane Murray Footway Improvement shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plots 1.4 and 1.9, unless and until details of Jane Murray Footway Improvement have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of the 50th dwelling on Plots 1.4 and 1.9 and prior to occupation of any dwelling on Plot P1.10, Jane Murray Footway Improvement shall be constructed. Not to occupy the 50th dwelling on Plots 1.4 and 1.9 and any dwelling on Plot P1.10, unless and until Jane Murray Footway Improvement has been constructed. | OPA Drawing: 60578790-ACM-XX-XX-DR-CE-000146-147 | Schedule 12, Part 8 | 102
A2300 Footway Improvements | Prior to commencement of development on Plots 1.4, 1.9, 1.10 or 1.11, details of the A2300 Footway Improvements shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plots 1.4, 1.9, 1.10 or 1.11 unless and until details of the A2300 Footway Improvements have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of any land use on Plots 1.4, 1.9, 1.10 or 1.11, the A2300 Footway Improvements shall be constructed. Not to occupy land use on Plots 1.4, 1.9, 1.10 or 1.11 unless and until the A2300 Footway Improvements has been constructed. | Prior to commencement development on Plots 1.4 and 1.9, details of A2300 Footway Improvementsshall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plots 1.4 and 1.9 unless and until details of A2300 Footway Improvements have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of the 50th dwelling on Plots 1.4 and 1.9 combined, A2300 Footway Improvements shall be constructed. Not to occupy the 50th dwelling on Plots 1.4 and 1.9, combined unless and until A2300 Footway Improvements has been constructed. | OPA Drawing: 60578790-ACM-XX-XX-DR-CE-000148-149 | Schedule 12, Part 8 | 102
Fairbridge Way Improvement Scheme | Prior to the occupation of the 400th dwelling, the Fairbridge Way Works shall be implemented. Not to occupy more than 399 dwellings unless and until the Fairbridge Way Works have been implemented. | Prior to the 50th dwelling occupation on Plots 1.7 and 1.8 combined the Fairbridge Way Works shall be implemented. Not to occupy the 50th dwelling on Plots 1.7 and 1.8 combined, unless and until the Fairbridge Way Works have been implemented. | Drawing from Transport Assessment Addendum: SK0017 | Schedule 12, Part 8 | 97
Fairbridge Way Temporary Pedestrian and Cycle Improvements | Prior to commencement of development on Plots 1.4, 1.9, 1.10 or 1.11, details of the Fairbridge Way Temporary Pedestrian and Cycle Improvements shall be submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Not to commence development on Plots 1.4, 1.9, 1.10 or 1.11 unless and until details of the Fairbridge Way Temporary Pedestrian and Cycle Improvements have been submitted to and approved in writing by the local planning authority. Development shall be carried out in accordance with the approved details. Prior to the occupation of any land use on Plots 1.4, 1.9, 1.10 or 1.11, the Fairbridge Way Temporary Pedestrian and Cycle Improvements shall be constructed. Works to last a maximum of three years before removal of following completion of the Northern Arc avenue whichever is the sooner. Not to occupy land use on Plots 1.4, 1.9, 1.10 or 1.11 unless and until the Fairbridge Way Temporary Pedestrian and Cycle Improvements has been constructed. Works to last a maximum of three years before removal of following completion of the Northern Arc avenue whichever is the sooner. |  |  | Schedule 12, Part 8 | 103

## Sch13 MSDC Obligations
Northern Arc, Burgess Hill Outline Planning Application S106 Obligations Tracker (Ref DM/23/0747) - Schedule 13 MSDC Obligations
Obligation Topic | Obligation wording | Proposed Obligation wording | Schedule | Reference (Paragraph No.) | Page | Notes
Community Sports Delivery Contribution | The District Council shall apply the Centre for Community Sports Maintenance Contribution to secure the long term maintenance of the Centre for Community Sports PROVIDED THAT the District Council may with the written approval of the Review Group secure the reapplication of no more than 25% of any paid part of the Centre for Community Sport Maintenance Contribution to secure any reasonable enhancement to maintenance of the facilities at the Triangle subject to the District Council providing written confirmation to the Owners that any such reapplication of the funds will not in any way materially impact upon the function, operation and overall quality of the Centre for Community Sports. | The District Council shall apply the Community Sports Delivery Contribution and any of the Centre for Outdoor Sport Maintenance Contribution spent on the delivery of the Sports Facilities to secure that facility in a timely and efficient manner to ensure that it is readily available to serve the needs of the development PROVIDED THAT the District Council may secure the reapplication of no more than 25% of any paid part of the Community Sports Delivery Contribution to support the provision of a new sports pitch and the reconfiguration of the car park at the Triangle subject to the District Council providing written confirmation to the Owners that any such reapplication of the funds will not in any way materially impact upon the function, operation and overall quality of the Centre for Outdoor Sports. | Schedule 13 Part 3 | 3.1 | 226
Community Sports Maintenance Contribution | The District Council shall apply the Centre for Community Sports Maintenance Contribution to secure the long term maintenance of the Centre for Community Sports PROVIDED THAT the District Council may with the written approval of the Review Group secure the reapplication of no more than 25% of any paid part of the Centre for Community Sports Maintenance Contribution to secure any reasonable enhancement to maintenance of the facilities at the Triangle subject to the District Council providing written confirmation to the Owners that any such reapplication of the funds will not in any way materially impact upon the function, operation and overall quality of the Centre for Community Sports. | The District Council shall apply the Centre for Outdoor Sports Maintenance Contribution (excluding any money spent on the delivery of the Sports Facilities) to secure the long term maintenance of the Centre for Outdoor Sports provided that the District Council may with the written approval of the Review Group secure the reapplication of no more than 25% of any paid part of the Centre for Outdoor Sports Maintenance Contribution to secure any reasonable enhancement to maintenance of the facilities at the Triangle subject to the District Council providing written confirmation that any such reapplication of the funds will not in any way materially impact upon the function, operation and overall quality of the Centre for Outdoor Sports. | Schedule 13 Part 3 | 3.2 | 226

## Sch15 Public Transport Strategy
Northern Arc, Burgess Hill Outline Planning Application S106 Obligations Tracker (Ref DM/23/0747) - Schedule 15 Public Transport Strategy
Obligation Topic | Obligation wording | Proposed Obligation wording | Schedule | Reference (Paragraph No.) | Page | Notes
Public Transport Strategy | The County Council covenants as follows: 2.1. To only apply the Public Transport Contribution for the purposes specified in this Deed and the Public Transport Strategy, in accordance with terms of the Public Transport Strategy. 2. 2. To bring the Bus Service into operation in accordance with the terms of the Public Transport Strategy such that it is available for use by the public prior to April 2023 and thereafter to use all reasonable endeavours to ensure that the Bus Service remains in operation and available for use by the public in accordance with the Public Transport Strategy. 2.3. To prepare and provide to the Owner a Public Transport Spending Report within 2 months of the date which is 12 months following the date on which the Public Transport Initial Contribution is received by the County Council. 2.4. Thereafter to prepare and provide to the Owner a Public Transport Spending Report within 2 months of the date which is 12 months following the date of the previous Public Transport Strategy Spending Report, until such time as the final Public Transport Phase Contribution has either been: 2.4.1. Spent (in its entirety) for the purposes identified in this Deed and the subject of a Public Transport Spending Report; or 2.4.2. Returned to the Owner pursuant to paragraph 2.5 of this Schedule 15. 2. 5. Where any part of the Public Transport Contribution remains unspent or uncommitted on the date which is three (3) years following the date on which the final Public Transport Phase Contribution is received by the County Council, to return such parts of the Public Transport Contribution. to the Owner." | The County Council covenants as follows: 2.1. To only apply the Public Transport Contribution for the purposes specified in this Deed and the Public Transport Strategy, in accordance with terms of the Public Transport Strategy. 2. 2. To bring the Bus Service into operation, in accordance with the terms of the Revised Public Transport Strategy (January 2026) or any amendment to the Public Transport Strategy agreed with WSCC & MSDC such that it is available for use by the public prior to April 2023 and thereafter to use all reasonable endeavours to ensure that the Bus Service remains in operation and available for use by the public in accordance with the Public Transport Strategy. 2.3. To prepare and provide to the Owner a Public Transport Spending Report within 2 months of the date which is 12 months following the date on which the Public Transport Initial Contribution is received by the County Council. 2.4. Thereafter to prepare and provide to the Owner a Public Transport Spending Report within 2 months of the date which is 12 months following the date of the previous Public Transport Strategy Spending Report, until such time as the final Public Transport Phase Contribution has either been: 2.4.1. Spent (in its entirety) for the purposes identified in this Deed and the subject of a Public Transport Spending Report; or 2.4.2. Returned to the Owner pursuant to paragraph 2.5 of this Schedule 15. 2. 5. Where any part of the Public Transport Contribution remains unspent or uncommitted on the date which is three (3) years following the date on which the final Public Transport Phase Contribution is received by the County Council, to return such parts of the Public Transport Contribution. to the Owner." | Schedule 15 | 2 | DoV Dec 22 p.28 &29 | Public Transport Strategy has been updated to include the dial a ride service.